## GBC PORTAL
Story ID | Role | Story Title | Theme | Written By | Priority | Complexity | MoSCoW | Points | Sprint | Reviewed On | Released On
US-GBC-001 | GBCS User | Create a resolution / proceeding | Resolution | JNVD | High | High | Must Do | 8 | 9 | 2016-12-27 | 2017-01-13
US-GBC-002 | GBCS User | Attach a Document | Resolution | JNVD | Medium | Medium | Must Do | 2 | 4 | 2016-12-27 | 2017-01-13
US-GBC-003 | GBCS User | Categorize the Resolution | Resolution | JNVD | Medium | Medium | Must Do | 2 | 4 | 2016-12-27 | 2017-01-13
US-GBC-004 | GBCS User | Tag the Resolution | Resolution | JNVD | Medium | Medium | Should Do | 3 | 16 | 2016-12-27 | 2017-01-13
US-GBC-005 | GBCS User | Set visibility of the resolution | Resolution | JNVD | Medium | Medium | Must Do | 3 | 16 | 2016-12-27 | 2017-01-13
US-GBC-006 | GBCS User | Allow / Disallow Comments | Resolution | JNVD | Low | Medium | Should Do | 1 | 11 | 2017-01-11 | 2017-01-13
US-GBC-007 | GBCS User | View Resolution List | Resolution | JNVD | High | Medium | Must Do | 1 | 2 | 2016-12-27 | 2017-01-13
US-GBC-008 | GBCS User | View Resolution (for Secretariat User) | Resolution | JNVD | High | Medium | Should Do | 2 | 10 | 2016-12-27 | 2017-01-13
US-GBC-009 | GBCS User | Edit the resolution | Resolution | JNVD | High | Medium | Should Do | 3 | 10 | 2017-01-02 | 2017-01-13
US-GBC-010 | GBCS User | Edit a published resolution | Resolution | JNVD | Medium | High | Should Do | 3 | 10 | 2017-01-02 | 2017-01-13
US-GBC-011 | GBCS Approver | Approve / Reject an edit to the published resolution | Resolution | JNVD | Medium | High | Could Do | 2 | 10 | 2017-01-02 | 2017-01-13
US-GBC-012 | GBCS User | Change Resolution Settings and Tags | Resolution | JNVD | Medium | Medium | Should Do | 5 | 9 | 2017-01-02 | 2017-01-13
US-GBC-013 | GBCS User | Validate the resolution | Resolution | JNVD | Medium | High | Should Do | 8 | 14 | 2017-01-02 | 2017-01-13
US-GBC-014 | GBCS User | Amend the Resolution | Resolution | JNVD | Medium | Medium | Should Do | 3 | 17 | 2017-01-11 | 2017-01-13
US-GBC-015 | GBCS User | Create a task | Action Items | JNVD | Medium | Medium | Should Do | 2 | 10 | 2017-01-02 | 2017-01-13
US-GBC-016 | GBCS User | Edit a task | Action Items | JNVD | Medium | Medium | Should Do | 2 | 16 | 2017-01-02 | 2017-01-13
US-GBC-017 | GBCS User | Track the task completion status | Action Items | JNVD | Medium | Medium | Should Do | 2 | 2 | 2017-01-02 | 2017-01-13
US-GBC-018 | Portal User | View the tasks | Action Items | JNVD | Medium | Medium | Should Do | 1 | 16 | 2017-01-02 | 2017-01-13
US-GBC-019 | Portal User | Update task status | Action Items | JNVD | Medium | Medium | Should Do | 2 | 2 | 2017-01-02 | 2017-01-13
US-GBC-020 | GBCS User | Create an Action Item for a Resolution | Action Items | JNVD | Medium | Medium | Should Do | 2 | 9 | 2017-01-02 | 2017-01-13
US-GBC-021 | GBCS User | Create task owner group | Action Items | JNVD | Medium | Medium | Should Do | 2 | 16 | 2017-01-11 | 2017-01-13
US-GBC-022 | GBCS User | Add / Remove members to a Task Owner Group | Action Items | JNVD | Medium | Medium | Should Do | 2 | 16 | 2017-01-11 | 2017-01-13
US-GBC-023 | Portal User | Search the Resolution (Google-like Search) | Search | JNVD | High | High | Must Do | 8 | 11 | 2017-01-02 | 2017-01-13
US-GBC-024 | Portal User | Advanced Search for the Resolutions | Search | JNVD | High | High | Must Do | 8 | 4 | 2017-01-02 | 2017-01-13
US-GBC-025 | Portal User | View Resolution from search | Search | JNVD | High | Medium | Must Do | 2 | 0 | 2017-01-02 | 2017-01-13
US-GBC-026 | Portal User | Add Comments on Resolutions | Search | JNVD | Low | Medium | Should Do | 1 | 2 | 2017-01-02 | 2017-01-13
US-GBC-027 | Administrator | Create User | User | JNVD | Medium | Medium | Must Do | 1 | 13 | 2017-01-02 | 2017-01-13
US-GBC-028 | Administrator | Change User Profile | User | JNVD | Medium | Medium | Should Do | 1 | 13 | 2017-01-02 | 2017-01-13
US-GBC-029 | Portal User | Change password | User | JNVD | Medium | Low | Should Do | 1 | 10 | 2017-01-02 | 2017-01-13
US-GBC-030 | Administrator | Reset password | User | JNVD | Medium | Low | Should Do | 1 | 12 | 2017-01-02 | 2017-01-13
US-GBC-031 | Administrator | Activate or Deactivate the user | User | JNVD | Medium | Low | Should Do | 1 | 12 | 2017-01-02 | 2017-01-13