## SP LILA
Story ID | Role | Story Title | Theme | Written By | Priority | Complexity | MoSCoW | Points | Sprint | Reviewed On | Released On
US-SP-001 | Volunteer | Create a Pastime | Pastime | JNVD |  |  | Should Do | 8 | 17 | 2017-01-11 | 2017-01-13
US-SP-002 | Volunteer | Categorize the Pastime and set appropriate tags | Pastime | JNVD |  |  | Should Do | 5 | 16 | 2017-01-11 | 2017-01-13
US-SP-003 | Volunteer | Submit the Pastime for Review | Pastime | JNVD |  |  | Should Do | 1 | 16 | 2017-01-11 | 2017-01-13
US-SP-004 | Volunteer | Make corrections to the pastime | Pastime | JNVD |  |  | Should Do | 5
US-SP-005 | Volunteer | Update or Modify the Keywords / Tags | Pastime | JNVD |  |  | Must Do | 2 | 16 | 2017-01-11 | 2017-01-13
US-SP-006 | Reviewer | Review a pastime to suggest title | Pastime | JNVD |  |  | Must Do | 5 | 18
US-SP-007 | Reviewer | Give feedback on a pastime | Pastime | JNVD |  |  | Should Do | 3
US-SP-008 | Reviewer | Setting visibility of a pastime | Pastime | JNVD |  |  | Must Do | 2 | 14 | 2016-12-07 | 2016-12-09
US-SP-009 | Reviewer | Release the pastime if it is difficult for me to review it | Pastime | JNVD |  |  | Must Do | 1 | 14 | 2016-12-07 | 2016-12-09
US-SP-010 | Reviewer | View the leader dashboard - see status of top 10 contributors | Pastime | JNVD |  |  | Must Do | 1 | 14 | 2016-12-07 | 2016-12-09
US-SP-011 | Reviewer | View the list of pastimes allocated to me for review | Pastime | JNVD |  |  | Must Do | 1 | 15 | 2016-12-07 | 2016-12-09
US-SP-012 | Reviewer | Fetch more pastimes if I have completed my quota to review | Pastime | JNVD |  |  | Could Do | 1 | 15 | 2016-12-07 | 2016-12-09
US-SP-013 | Reviewer | View the list of pastimes for which I have submitted the review | Pastime | JNVD |  |  | Must Do | 1 | 15 | 2016-12-07 | 2016-12-09
US-SP-014 | Approver | View all the suggested titles | Pastime | JNVD |  |  | Should Do | 1 | 15 | 2016-12-07 | 2016-12-09
US-SP-015 | Approver | Approve the Suggested Title | Pastime | JNVD |  |  | Should Do | 1 | 15 | 2016-12-07 | 2016-12-09
US-SP-016 | Approver | Make corrections to the title and approve | Pastime | JNVD |  |  | Should Do | 3 | 18 | 2017-01-27 | 2017-01-27
US-SP-017 | Approver | Edit the Pastimes | Pastime | JNVD |  |  | Could Do | 2
US-SP-018 | Visitor | Search the pastime with a specific keyword(s) | Pastime | JNVD |  |  | Must Do | 5 | 13 | 2016-12-07 | 2016-12-09
US-SP-019 | Visitor | Advanced search for the pastime | Pastime | JNVD |  |  | Should Do | 3