## Projects
QUARTER 1 | 1 | 2 | 3 | 4 | 5 | 6 | APRIL 2017 | [6 empty] | MAY 2017 | [6 empty] | JUNE 2017
PROJECTS | [6 empty] | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
GBC PORTAL | [12 empty] | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 |  |  |  |  | 1 | 2 | 3
SATVATA | [6 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 4 | 5 | 6 | 7 | 8 | 9 | 10
SADHANA MODULE | [6 empty] | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 11 | 12 | 13 | 14 | 15 | 16 | 17
SERVICE DESK & IT IMS | [6 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TEMPLE DASHBOARD | [6 empty] | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 28 | 29 | 30 | 31 |  |  |  | 25 | 26 | 27 | 28 | 29 | 30
SRILA PRABHUPADA LILA | [6 empty] | 30
ISKCON WORLD
ISKCONBANGALORE.ORG
DHANAJAYA
LEARNING
AGILE
MONGODB
GRAILS
ANGULARJS

## Epics
S. No. | Project | Epic | SPRINT 1 | SPRINT 2 | SPRINT 3 | SPRINT 4 | SPRINT 5 | SPRINT 6
1001 | GBC PORTAL | ???
2001 | SATVATA | ???
3001 | SADHANA MODULE | USER PROFILE
3002 | SADHANA MODULE | DATA LOADING
3003 | SADHANA MODULE | SADHANA REPORTS
3004 | SADHANA MODULE | SADHANA REGULARIZATION
3005 | SADHANA MODULE | GRHASTA ALLOWANCE
4001 | SERVICE DESK & IT IMS | USER MANAGEMENT
4002 | SERVICE DESK & IT IMS | STORE MANAGEMENT
4003 | SERVICE DESK & IT IMS | VENDOR MANAGEMENT
4004 | SERVICE DESK & IT IMS | ACCESS MANAGEMENT
4005 | SERVICE DESK & IT IMS | SERVICE CATALOG MANAGEMENT
4006 | SERVICE DESK & IT IMS | APP ACCESS MANAGEMENT
4007 | SERVICE DESK & IT IMS | ASSET MANAGEMENT
4008 | SERVICE DESK & IT IMS | SERVICE DESK
4009 | SERVICE DESK & IT IMS | IT CONSOLE FOR USERS
4010 | SERVICE DESK & IT IMS | IT POLICY REPOSITORY
5001 | TEMPLE DASHBOARD | CHANTERS CLUB
5002 | TEMPLE DASHBOARD | HARINAM MANTAPA
5003 | TEMPLE DASHBOARD | NITYA ANNADANA
5004 | TEMPLE DASHBOARD | KICCHADI DISTRIBUTION
5005 | TEMPLE DASHBOARD | VISITOR DASHBOARD
5006 | TEMPLE DASHBOARD | REVIEW DATABASE
5007 | TEMPLE DASHBOARD | ONLINE DONATIONS
5008 | TEMPLE DASHBOARD | ONLINE CONTACTS
6001 | SRILA PRABHUPADA LILA | ???
7001 | ISKCON WORLD | GITA QUIZ
7002 | ISKCON WORLD | KRISHNA COSTUME CONTEST
8001 | ISKCON BANGALORE | CULTURE CAMP
8002 | ISKCON BANGALORE | HERITAGE FEST

## Sprint 1
US ID | User Story | Project | Story points | Kanhu | Abhilash | Anudeep | Guru | Basavaraj | Sreedhar | Requirements | Design | Data Migration | Screen Design | Coding | Code Review | Testing | Acceptance
| Edit Sadhana Points | SADHANA | 3 | [9 empty] | BK | SS | AD | AD | JNVD
| Edit Sadhana Excuse | SADHANA | 3 | [9 empty] | BK | SS | AD | AD | JNVD
| Override Sadhana Points | SADHANA | 3 | [9 empty] | BK | SS | AD | AD | JNVD
| View Sadhana Points | SADHANA | 3 | [9 empty] | BK | BK | AD | AD | JNVD
| Export Sadhana Details | SADHANA | 2 | [9 empty] | SS | SS | AD | AD | JNVD
| Login to Sadhana Module | SADHANA | 3 | [9 empty] | BK | SS | AD | AD | JNVD
| Migrate Sadhana Data | SADHANA | 5 | [6 empty] | JNVD |  |  | SS | SS | AD | AD | JNVD
| Display stock | IT IMS | 2 | [7 empty] | SS | JNVD | GP | GP | AD | AD | JNVD
| Issue Item | IT IMS | 2 | [9 empty] | AB | AB | AD | AD | JNVD
| Handle Item Returns | IT IMS | 2 | [9 empty] | AB | AB | AD | AD | JNVD
| Receive Item | IT IMS | 2 | [9 empty] | AB | AB | AD | AD | JNVD
| View Invoice | IT IMS | 2 | [6 empty] | JNVD | JNVD | JNVD | GP | GP | AD | AD | JNVD
| Approve Vendor | IT IMS | 1 | [9 empty] | AN | AN | AD | AD | JNVD
| Reject Vendor | IT IMS | 1 | [9 empty] | AN | AN | AD | AD | JNVD
| Deactivate Vendor Contact | IT IMS | 1 | [9 empty] | AN | AN | AD | AD | JNVD
| View Application Users List | IT IMS | 1 | [6 empty] | JNVD | JNVD | SS | GP | GP | AD | AD | JNVD
| Add an Asset | IT IMS | 2 | [9 empty] | GP | GP | AD | AD | JNVD
| Edit Asset Details | IT IMS | 2 | [9 empty] | GP | GP | AD | AD | JNVD
| Filter Asset List | IT IMS | 2 | [9 empty] | GP | GP | AD | AD | JNVD
| Raise a Ticket | SERVICE DESK | 2 | [6 empty] | JNVD | JNVD |  | KG | KG | AD | AD | JNVD
| Categorize a Ticket | SERVICE DESK | 2 | [6 empty] | JNVD | JNVD |  | KG | KG | AD | AD | JNVD
| Filter Ticket Details | SERVICE DESK | 2 | [6 empty] | JNVD | JNVD |  | KG | KG | AD | AD | JNVD
| View Assigned Tickets (Engineer) | SERVICE DESK | 2 | [6 empty] | JNVD | JNVD |  | KG | KG | AD | AD | JNVD
| Update Progress | SERVICE DESK | 2 | [6 empty] | JNVD | JNVD |  | KG | KG | AD | AD | JNVD
| Close a Ticket | SERVICE DESK | 2 | [6 empty] | JNVD | JNVD |  | KG | KG | AD | AD | JNVD
| Put a ticket on Hold | SERVICE DESK | 2 | [6 empty] | JNVD | JNVD |  | KG | KG | AD | AD | JNVD
| Cancel a Ticket | SERVICE DESK | 2 | [6 empty] | JNVD | JNVD |  | KG | KG | AD | AD | JNVD
| Reopen a Ticket | SERVICE DESK | 2 | [6 empty] | JNVD | JNVD |  | KG | KG | AD | AD | JNVD
| Assign / Reassign the Ticket | SERVICE DESK | 2 | [6 empty] | JNVD | JNVD |  | KG | KG | AD | AD | JNVD
| Import Contact Details | DASHBOARD | 3 | [9 empty] | SS | SS | AD | AD | JNVD
| View Donor Details | DASHBOARD | 2 | [9 empty] | BK | BK | AD | AD | JNVD
| View Review from various sources | DASHBOARD | 2 | [9 empty] | BK | BK | AD | AD | JNVD
| Understand how to export data to excel from list page | Training |  | 4 | 4 | 4 | 4 |  | 2
| Understand the user module functionality | Training |  | 4 | 4 | 4 | 4 |  | 2
| Understand how to do code review | Training |  | 4 | 4 | 4 | 4 | 4 | 4
| Training on Grails | Training |  | 4 | 4 | 4 | 4 | 4 | 4
| Total Hours |  |  | 16 | 16 | 16 | 16 | 8 | 12
| Available Hours |  |  | 132 | 140 | 140 | 98 | 140 | 132