## Stakeholder Requirements
# | Requested By | Request Description | Action | Action By | Target Date | Status
1 | Yuvaraj | Validity of resolutions to be updated so that the reurring resolutions that has to be re-tabled can be tracked as per the duration. | Validity - List having No Validation, 3/6/9 months, 1/2/3 yrs; based on this dates to be maintained. Snooze provision to be provided.
2 | SGCP | If it’s a proceeding, then resolution fields are not valid. | All other fields related to resolution will get disabled & mandatory checks should not happen.
3 | JNVP | Topics will be discussed in meetings, not reolution. Hence, should rename the # properly. | Resolution No. - Change as Topic No.
4 | SGCP | Field should be available to update whether Dissemination of the resolution is required, so that the centers can see and disseminate the resolution passed. | Field to be added as Disseminate To as part of the Applicable Tags section - Text will be added for which all branches they can dessiminate the resolution.
5 | SGCP | Field should be added to capture the SPOC name of team who will implement the resolutions made. This is optional. | Field to be added as Implementation Agency as part of the Applicable Tags section -
6 | JNVP | Change the caption for resolution action item as: | Do you want to convert this resolution to an action item?
7 | JNVP | The size of | Browse & Save button blocks should be same size.
8 | SGCP | Centers - All Center should be one of the tag option. | To be brainstormed.
9 | SGCP | Action Items to have target date enabled/disabled.
10 | JNVP | Better look and feel for Voting
11 |  | To be checked on change in design.