## Projects
QUARTER 1 | 1 | 2 | 3 | 4 | 5 | 6 | APRIL 2017 | [6 empty] | MAY 2017 | [6 empty] | JUNE 2017
PROJECTS | [6 empty] | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
GBC PORTAL | [12 empty] | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 |  |  |  |  | 1 | 2 | 3
SATVATA | [6 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 4 | 5 | 6 | 7 | 8 | 9 | 10
SADHANA MODULE | [6 empty] | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 11 | 12 | 13 | 14 | 15 | 16 | 17
SERVICE DESK & IT IMS | [6 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TEMPLE DASHBOARD | [6 empty] | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 28 | 29 | 30 | 31 |  |  |  | 25 | 26 | 27 | 28 | 29 | 30
SRILA PRABHUPADA LILA | [6 empty] | 30
ISKCON WORLD
ISKCONBANGALORE.ORG | [6 empty] | JULY 2017 | [6 empty] | AUGUST 2017 | [6 empty] | SEPTEMBER 2017
DHANAJAYA | [6 empty] | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
LEARNING | [12 empty] | 1 |  |  | 1 | 2 | 3 | 4 | 5 | [5 empty] | 1 | 2
AGILE | [6 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 3 | 4 | 5 | 6 | 7 | 8 | 9
MONGODB | [6 empty] | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 10 | 11 | 12 | 13 | 14 | 15 | 16
GRAILS | [6 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 17 | 18 | 19 | 20 | 21 | 22 | 23
ANGULARJS | [6 empty] | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 27 | 28 | 29 | 30 | 31 |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30
[7 empty] | 30 | 31

## Epics
S. No. | Project | Epic | SPRINT 1 | SPRINT 2 | SPRINT 3 | SPRINT 4 | SPRINT 5 | SPRINT 6
1001 | GBC PORTAL | ???
2001 | SATVATA | ???
3001 | SADHANA MODULE | USER PROFILE
3002 | SADHANA MODULE | DATA LOADING
3003 | SADHANA MODULE | SADHANA REPORTS
3004 | SADHANA MODULE | SADHANA REGULARIZATION
3005 | SADHANA MODULE | GRHASTA ALLOWANCE
4001 | SERVICE DESK & IT IMS | USER MANAGEMENT
4002 | SERVICE DESK & IT IMS | STORE MANAGEMENT
4003 | SERVICE DESK & IT IMS | VENDOR MANAGEMENT
4004 | SERVICE DESK & IT IMS | ACCESS MANAGEMENT
4005 | SERVICE DESK & IT IMS | SERVICE CATALOG MANAGEMENT
4006 | SERVICE DESK & IT IMS | APP ACCESS MANAGEMENT
4007 | SERVICE DESK & IT IMS | ASSET MANAGEMENT
4008 | SERVICE DESK & IT IMS | SERVICE DESK
4009 | SERVICE DESK & IT IMS | IT CONSOLE FOR USERS
4010 | SERVICE DESK & IT IMS | IT POLICY REPOSITORY
5001 | TEMPLE DASHBOARD | CHANTERS CLUB
5002 | TEMPLE DASHBOARD | HARINAM MANTAPA
5003 | TEMPLE DASHBOARD | NITYA ANNADANA
5004 | TEMPLE DASHBOARD | KICCHADI DISTRIBUTION
5005 | TEMPLE DASHBOARD | VISITOR DASHBOARD
5006 | TEMPLE DASHBOARD | REVIEW DATABASE
5007 | TEMPLE DASHBOARD | ONLINE DONATIONS
5008 | TEMPLE DASHBOARD | ONLINE CONTACTS
6001 | SRILA PRABHUPADA LILA | ???
7001 | ISKCON WORLD | GITA QUIZ
7002 | ISKCON WORLD | KRISHNA COSTUME CONTEST
8001 | ISKCON BANGALORE | CULTURE CAMP
8002 | ISKCON BANGALORE | HERITAGE FEST

## Sprint 1
US ID | User Story | Project | Story points | Kanhu | Abhilash | Anudeep | Guru | Basavaraj | Sreedhar
| Edit Sadhana Points | SADHANA | 3
| Edit Sadhana Excuse | SADHANA | 3
| Override Sadhana Points | SADHANA | 3
| View Sadhana Points | SADHANA | 3
| Export Sadhana Details | SADHANA | 2
| Login to Sadhana Module | SADHANA | 3
| Migrate Sadhana Data | SADHANA | 5
| Display stock | IT IMS | 2
| Issue Item | IT IMS | 2
| Handle Item Returns | IT IMS | 2
| Receive Item | IT IMS | 2
| View Invoice | IT IMS | 2
| Approve Vendor | IT IMS | 1
| Reject Vendor | IT IMS | 1
| Deactivate Vendor Contact | IT IMS | 1
| View Application Users List | IT IMS | 1
| Add an Asset | IT IMS | 2
| Edit Asset Details | IT IMS | 2
| Filter Asset List | IT IMS | 2
| Raise a Ticket | SERVICE DESK | 2
| Categorize a Ticket | SERVICE DESK | 2
| Filter Ticket Details | SERVICE DESK | 2
| View Assigned Tickets (Engineer) | SERVICE DESK | 2
| Update Progress | SERVICE DESK | 2
| Close a Ticket | SERVICE DESK | 2
| Put a ticket on Hold | SERVICE DESK | 2
| Cancel a Ticket | SERVICE DESK | 2
| Reopen a Ticket | SERVICE DESK | 2
| Assign / Reassign the Ticket | SERVICE DESK | 2
| Import Contact Details | DASHBOARD | 3
| View Donor Details | DASHBOARD | 2
| View Review from various sources | DASHBOARD | 2
| Understand how to export data to excel from list page | Training |  | 4 | 4 | 4 | 4 |  | 2
| Understand the user module functionality | Training |  | 4 | 4 | 4 | 4 |  | 2
| Understand how to do code review | Training |  | 4 | 4 | 4 | 4 | 4 | 4
| Training on Grails | Training |  | 4 | 4 | 4 | 4 | 4 | 4
| Total Hours |  |  | 16 | 16 | 16 | 16 | 8 | 12
| Available Hours |  |  | 132 | 140 | 140 | 98 | 140 | 132
69

## Task List
S.No. | Task | Who | Dependencies | Started On | Completed On
1 | Screen Design for Edit Sadhana Points | BK |  | 2017-04-03
2 | Coding for Edit Sadhana Points | SS
3 | Code Review for Edit Sadhana Points | AD | 1, 2
4 | Testing for Edit Sadhana Points | AD | 3
5 | Acceptance for Edit Sadhana Points | JNVD | 4
6 | Screen Design for Edit Sadhana Excuse | BK |  | 2017-04-03
7 | Coding for Edit Sadhana Excuse | SS
8 | Code Review for Edit Sadhana Excuse | AD | 6, 7
9 | Testing for Edit Sadhana Excuse | AD | 8
10 | Acceptance for Edit Sadhana Excuse | JNVD | 9
11 | Screen Design for Override Sadhana Points | BK |  | 2017-04-03
12 | Coding for Override Sadhana Points | SS
13 | Code Review for Override Sadhana Points | AD | 11, 12
14 | Testing for Override Sadhana Points | AD | 13
15 | Acceptance for Override Sadhana Points | JNVD | 14
16 | Screen Design for View Sadhana Points | BK
17 | Coding for View Sadhana Points | SS
18 | Code Review for View Sadhana Points | AD | 16, 17
19 | Testing for View Sadhana Points | AD | 18
20 | Acceptance for View Sadhana Points | JNVD | 19
21 | Screen Design for Export Sadhana Details | SS
22 | Coding for Export Sadhana Details | SS
23 | Code Review for Export Sadhana Details | AD | 21, 22
24 | Testing for Export Sadhana Details | AD | 23
25 | Acceptance for Export Sadhana Details | JNVD | 24
26 | Understand the user module functionality | SS |  | 2017-04-04
27 | Screen Design for Login to Sadhana Module | BK | 26
28 | Coding for Login to Sadhana Module | SS | 26
29 | Code Review for Login to Sadhana Module | AD | 27, 28
30 | Testing for Login to Sadhana Module | AD | 29
31 | Acceptance for Login to Sadhana Module | JNVD | 30
32 | Migration for Sadhana Data | JNVD / SS
33 | Get Stock Data | JNVD
34 | Screen Design for Display stock | GP |  | 2017-04-03
35 | Coding for Display stock | GP |  | 2017-04-03
36 | Code Review for Display stock | AD | 34, 35
37 | Testing for Display stock | AD | 36
38 | Acceptance for Display stock | JNVD | 37
39 | Screen Design for Issue Item | AB
40 | Coding for Issue Item | AB
41 | Code Review for Issue Item | AD | 39, 40
42 | Testing for Issue Item | AD | 41
43 | Acceptance for Issue Item | JNVD | 42
44 | Screen Design for Handle Item Returns | AB
45 | Coding for Handle Item Returns | AB
46 | Code Review for Handle Item Returns | AD | 44, 45
47 | Testing for Handle Item Returns | AD | 46
48 | Acceptance for Handle Item Returns | JNVD | 47
49 | Screen Design for Receive Item | AB
50 | Coding for Receive Item | AB
51 | Code Review for Receive Item | AD | 49, 50
52 | Testing for Receive Item | AD | 51
53 | Acceptance for Receive Item | JNVD | 52
54 | Update invoice data in current IT IMS & Clean up | Nithya / JNVD
55 | Design for Invoice | JNVD
56 | Screen Design for View Invoice | GP | 55
57 | Coding for View Invoice | GP | 55
58 | Code Review for View Invoice | AD | 56, 57
59 | Testing for View Invoice | AD | 58
60 | Acceptance for View Invoice | JNVD | 59
61 | Screen Design for Approve Vendor | AN
62 | Coding for Approve Vendor | AN
63 | Code Review for Approve Vendor | AD | 61, 62
64 | Testing for Approve Vendor | AD | 63
65 | Acceptance for Approve Vendor | JNVD | 64
66 | Screen Design for Reject Vendor | AN
67 | Coding for Reject Vendor | AN
68 | Code Review for Reject Vendor | AD | 66, 67
69 | Testing for Reject Vendor | AD | 68
70 | Acceptance for Reject Vendor | JNVD | 69
71 | Screen Design for Deactivate Vendor Contact | AN
72 | Coding for Deactivate Vendor Contact | AN
73 | Code Review for Deactivate Vendor Contact | AD | 71, 72
74 | Testing for Deactivate Vendor Contact | AD | 73
75 | Acceptance for Deactivate Vendor Contact | JNVD | 74
76 | Data Migration for View Application Users List | SS
77 | Screen Design for View Application Users List | GP
78 | Coding for View Application Users List | GP
79 | Code Review for View Application Users List | AD | 77, 78
80 | Testing for View Application Users List | AD | 79
81 | Acceptance for View Application Users List | JNVD | 80
82 | Screen Design for Add an Asset | GP |  | 2017-04-03
83 | Coding for Add an Asset | GP |  | 2017-04-03
84 | Code Review for Add an Asset | AD | 82, 83
85 | Testing for Add an Asset | AD | 84
86 | Acceptance for Add an Asset | JNVD | 85
87 | Screen Design for Edit Asset Details | GP |  | 2017-04-03
88 | Coding for Edit Asset Details | GP |  | 2017-04-03
89 | Code Review for Edit Asset Details | AD | 87, 88
90 | Testing for Edit Asset Details | AD | 89
91 | Acceptance for Edit Asset Details | JNVD | 90
92 | Screen Design for Filter Asset List | GP
93 | Coding for Filter Asset List | GP
94 | Code Review for Filter Asset List | AD | 92, 93
95 | Testing for Filter Asset List | AD | 94
96 | Acceptance for Filter Asset List | JNVD | 95
97 | Write User stories for Service Desk Features | JNVD
98 | Finalize design for Service Desk | JNVD
99 | Screen Design for Raise a Ticket | KG | 97, 98
100 | Coding for Raise a Ticket | KG | 97, 98
101 | Code Review for Raise a Ticket | AD | 99, 100
102 | Testing for Raise a Ticket | AD | 101
103 | Acceptance for Raise a Ticket | JNVD | 102
104 | Screen Design for Categorize a Ticket | KG | 97, 98
105 | Coding for Categorize a Ticket | KG | 97, 98
106 | Code Review for Categorize a Ticket | AD | 104, 105
107 | Testing for Categorize a Ticket | AD | 106
108 | Acceptance for Categorize a Ticket | JNVD | 107
109 | Screen Design for Filter Ticket Details | KG | 97, 98
110 | Coding for Filter Ticket Details | KG | 97, 98
111 | Code Review for Filter Ticket Details | AD | 109, 110
112 | Testing for Filter Ticket Details | AD | 111
113 | Acceptance for Filter Ticket Details | JNVD | 112
114 | Screen Design for View Assigned Tickets (Engineer) | KG | 97, 98
115 | Coding for View Assigned Tickets (Engineer) | KG | 97, 98
116 | Code Review for View Assigned Tickets (Engineer) | AD | 114, 115
117 | Testing for View Assigned Tickets (Engineer) | AD | 116
118 | Acceptance for View Assigned Tickets (Engineer) | JNVD | 117
119 | Screen Design for Update Progress | KG | 97, 98
120 | Coding for Update Progress | KG | 97, 98
121 | Code Review for Update Progress | AD | 119, 120
122 | Testing for Update Progress | AD | 121
123 | Acceptance for Update Progress | JNVD | 122
124 | Screen Design for Close a Ticket | KG | 97, 98
125 | Coding for Close a Ticket | KG | 97, 98
126 | Code Review for Close a Ticket | AD | 124, 125
127 | Testing for Close a Ticket | AD | 126
128 | Acceptance for Close a Ticket | JNVD | 127
129 | Screen Design for Put a ticket on Hold | KG | 97, 98
130 | Coding for Put a ticket on Hold | KG | 97, 98
131 | Code Review for Put a ticket on Hold | AD | 129, 130
132 | Testing for Put a ticket on Hold | AD | 131
133 | Acceptance for Put a ticket on Hold | JNVD | 132
134 | Screen Design for Cancel a Ticket | KG | 97, 98
135 | Coding for Cancel a Ticket | KG | 97, 98
136 | Code Review for Cancel a Ticket | AD | 134, 135
137 | Testing for Cancel a Ticket | AD | 136
138 | Acceptance for Cancel a Ticket | JNVD | 137
139 | Screen Design for Reopen a Ticket | KG | 97, 98
140 | Coding for Reopen a Ticket | KG | 97, 98
141 | Code Review for Reopen a Ticket | AD | 139, 140
142 | Testing for Reopen a Ticket | AD | 141
143 | Acceptance for Reopen a Ticket | JNVD | 142
144 | Screen Design for Assign / Reassign the Ticket | KG | 97, 98
145 | Coding for Assign / Reassign the Ticket | KG | 97, 98
146 | Code Review for Assign / Reassign the Ticket | AD | 144, 145
147 | Testing for Assign / Reassign the Ticket | AD | 146
148 | Acceptance for Assign / Reassign the Ticket | JNVD | 147
149 | Screen Design for Import Contact Details | SS
150 | Coding for Import Contact Details | SS
151 | Code Review for Import Contact Details | AD | 149, 150
152 | Testing for Import Contact Details | AD | 151
153 | Acceptance for Import Contact Details | JNVD | 152
154 | Screen Design for View Donor Details | BK
155 | Coding for View Donor Details | BK
156 | Code Review for View Donor Details | AD | 154, 155
157 | Testing for View Donor Details | AD | 156
158 | Acceptance for View Donor Details | JNVD | 157
159 | Screen Design for View Review from various sources | BK
160 | Coding for View Review from various sources | BK
161 | Code Review for View Review from various sources | AD | 159, 160
162 | Testing for View Review from various sources | AD | 161
163 | Acceptance for View Review from various sources | JNVD | 162
164 | Understand how to export data to excel from list page | ALL |  | 2017-04-04
162 | Understand how to do code review | ALL
163 | Training on Grails | ALL |  | 2017-04-10